PROJECT CHARTER

Customer Digital Portal (PRJ-101)

Fictional enterprise case study | Version 1.0 | Status date: 23 October 2026

# 1. Executive Summary

The Customer Digital Portal programme will provide customers with a secure, accessible digital channel for common servicing journeys. The initiative aims to reduce avoidable contact-centre demand, improve customer experience, and create a maintainable foundation for future digital services. This charter authorises planning and delivery activities for the defined scope; it does not constitute approval to exceed the approved budget or bypass security, privacy, or operational controls.

# 2. Business Problem and Opportunity

Customers currently rely on a mix of assisted channels and fragmented digital journeys. This creates avoidable effort for customers and service teams, inconsistent status visibility, and limited ability to measure completion across journeys. A unified portal is expected to improve self-service while preserving appropriate assisted support for complex or sensitive cases.

# 3. Objectives and Success Measures

| Objective | Measure | Initial target |
| --- | --- | --- |
| Improve self-service completion | Successful completion rate for in-scope journeys | At least 80% in pilot |
| Reduce avoidable support demand | Contact rate for portal-supported journeys | 10% reduction within 3 months of launch |
| Deliver a stable service | Critical defects at go-live | Zero open Severity 1 defects |
| Protect customer information | High-risk security/privacy findings at go-live | Zero unresolved critical findings |
| Maintain financial control | Forecast cost against approved baseline | Within EUR 1,250,000 approved budget unless formally re-baselined |

# 4. Scope

## In scope

Responsive customer portal for agreed servicing journeys.

Identity-provider integration and role-based access.

Integration with approved customer and case-status APIs.

Accessibility, functional, integration, security, and user-acceptance testing.

Operational handover, monitoring, support runbook, and release readiness.

## Out of scope

Replacement of core customer-record systems.

Unapproved use of customer data for model training or analytics.

Additional customer journeys not approved through change control.

Automatic production changes without authorised human approval.

# 5. Key Deliverables

Approved requirements and user journeys.

Portal application and API integrations.

Test evidence, defect triage records, and UAT exit recommendation.

Security/privacy assessment and operational readiness pack.

Deployment plan, rollback plan, and post-launch measurement dashboard.

# 6. Governance and Responsibilities

| Role | Accountability | Decision rights |
| --- | --- | --- |
| Executive Sponsor | Business outcomes, funding, priority trade-offs | Approve material scope/funding changes |
| Project Manager | Plan, delivery coordination, status, RAID and escalation | Manage within approved tolerances |
| Product Owner | Requirements, prioritisation, acceptance | Accept in-scope product increments |
| Solution Architect | Architecture, integration, non-functional requirements | Recommend technical design and exceptions |
| Security & Privacy | Control requirements and assurance | Approve or reject control exceptions within mandate |
| QA Lead | Test strategy, defect management, UAT evidence | Recommend test exit based on agreed criteria |

# 7. High-Level Plan and Milestones

The status dataset dated 23 October 2026 reports identity integration defects as the principal near-term constraint. The current forecast for UAT exit is 20 November 2026 and forecast production release is 8 January 2027, compared with a baseline release date of 18 December 2026. These are planning forecasts, not commitments; the project team must update them using approved schedule controls.

# 8. Budget and Financial Controls

Approved budget: EUR 1,250,000. Actual cost reported at 23 October 2026: EUR 812,500. Current forecast cost: EUR 1,210,000. The Project Manager will refresh the estimate at completion monthly and explain material variances. Any forecast above the approved budget requires a documented options analysis and sponsor decision before commitment.

# 9. Assumptions and Constraints

Required identity and customer APIs will be available in agreed test environments.

Business representatives will be available for requirements clarification and UAT.

Customer data access will follow least-privilege, privacy, retention, and audit requirements.

The delivery team will use approved enterprise tools and change-control processes.

# 10. High-Level Risks and Responses

Identity integration defects may compress UAT: daily triage and specialist support decision by 30 October 2026.

Late changes may expand scope: apply formal change control and assess cost/schedule/quality impacts.

Security or privacy findings may block release: complete control validation before go-live approval.

# 11. Acceptance and Approval

The charter is a fictional training artifact. In a live project, approval would be recorded by the Executive Sponsor and relevant control owners before the project proceeds beyond the authorised stage.

| Approver role | Name / signature | Date |
| --- | --- | --- |
| Executive Sponsor | Pending | Pending |
| Project Manager | Pending | Pending |
| Business Owner | Pending | Pending |