WEEKLY PROJECT STATUS REPORT

Customer Digital Portal | PRJ-101 | Fictional case study

Reporting date: 23 October 2026 | Report owner: Maya Patel, Project Manager

# 1. Executive Summary

Overall status is AMBER. Delivery remains achievable, but identity-provider integration defects are compressing the available User Acceptance Testing (UAT) window. The forecast production release is 8 January 2027, compared with the baseline date of 18 December 2026. Budget remains GREEN based on the current forecast, with EUR 1,210,000 forecast against an approved EUR 1,250,000.

# 2. RAG Status

| Dimension | Status | Comment |
| --- | --- | --- |
| Overall | AMBER | Recovery action required to protect UAT |
| Schedule | AMBER | Forecast release is 3 weeks later than baseline |
| Budget | GREEN | Forecast is EUR 40,000 below approved budget |
| Scope | GREEN | No approved scope change reported |
| Risk | AMBER | Identity integration defects remain the top risk |

# 3. Progress and Financials

| Metric | Value | Interpretation |
| --- | --- | --- |
| Planned progress | 72% | Baseline expectation as of report date |
| Actual progress | 64% | 8 percentage points behind plan |
| Approved budget | EUR 1,250,000 | Current approved baseline |
| Actual cost | EUR 812,500 | Cost recorded to reporting date |
| Forecast cost | EUR 1,210,000 | EUR 40,000 headroom to budget |

# 4. Key Milestones

| Milestone | Baseline | Current forecast | Status |
| --- | --- | --- | --- |
| Identity integration complete | 16 Oct 2026 | 30 Oct 2026 | AMBER |
| UAT exit | 13 Nov 2026 | 20 Nov 2026 | AMBER |
| Production release | 18 Dec 2026 | 8 Jan 2027 | AMBER |

# 5. Top Risks, Issues and Actions

| Item | Impact | Owner | Action / due date |
| --- | --- | --- | --- |
| Identity-provider integration defects | May reduce UAT duration and delay release | Platform Lead | Daily defect triage; review trend by 30 Oct |
| Regression test window pressure | Potential quality risk | QA Lead | Prioritise critical journeys; confirm test window by 6 Nov |
| Late specialist support decision | May prolong defect resolution | Project Manager / Sponsor | Decide on two-week support if trend does not improve by 30 Oct |

# 6. Decisions Required

Decision: approve two weeks of specialist identity-integration support if the critical-defect trend has not improved by 30 October 2026. Decision owner: Executive Sponsor. Decision needed by: 30 October 2026.

# 7. Next Reporting Period

Reduce open critical identity-integration defects and publish daily trend.

Confirm UAT entry criteria, test data, and business tester availability.

Refresh release forecast after the 30 October defect review.

Keep scope changes under formal change control.

# 8. Governance Note

This report is a synthetic training artifact. Statuses and figures are illustrative and should not be treated as information about a real organisation or client.